## Sprint Backlog
Sprint Back Log
Task ID | Task | Description | Story ID | Backlog ID | Sprint# | State | Estimate Time (Hours) | Assign to | Note
SMS Manage
T01 | Draw Usecase SMS |  |  | PB01 |  | New | 40 | Huy Hưng
T02 | Analyse and design code SMS |  |  |  |  | New | 40 | Huy Hưng
T03 | Code : Update start date and end date of single quarantee period |  | RQ04 |  | 1 | New | 10 | Hưng
T04 | Code: Set up SMS form |  |  |  | 1 | New | 2 | Hưng
T05 | Code: Send SMS |  | RQ05 |  | 1 | New | 25 | Huy
T06 | Code: Save SMS list , which have been sent for customer |  | RQ10 |  | 1 | New | 20 | Hưng
T07 | Code: View SMS list, which have been sent for customer |  |  |  | 1 | New | 10 | Hưng
T08 | Set up, update time to send SMS and time to stop send SMS |  |  |  | 1 | New | 30 | Hưng
T09 | Integrate All functions SMS | [5 empty] | 10 | Huy Hưng
T10 | Implement Unit Test , Integrated Test , System Test SMS |  |  |  | 1 | New | 30 | Huy Hưng
Customer Manage
T11 | Draw Usecase Customer Manage |  |  | PB02 |  |  | 20 | Tuấn
T12 | Analyse and design codeCustomer Manage | [5 empty] | 20 | Tuấn
T13 | Code: Import customer from excel format |  | RQ02 RQ03 |  | 1 | New | 20 | Tuấn Thắng
T14 | Code: Add new customer |  |  |  | 1 | New | 15 | Tuấn
T15 | Code: Update customer |  |  |  | 1 | New | 10 | Tuấn
T16 | Code: Disable customer |  |  |  | 1 | New | 5 | Tuấn
T17 | Code: Find Customer |  |  |  | 1 | New | 10 | Tuấn
T18 | Code: Set up time range that user can view list of customer birthday |  | RQ07 |  | 1 | New | 15 | Tuấn Thắng
T19 | Code: Print recent BirthDay Customer list |  |  |  | 1 | New | 20 | Tuấn Thắng
T20 | Code: View recent BirthDay Customer list |  |  |  | 1 | New | 5 | Tuấn Thắng
T21 | Integrate All functions Customer Manage |  |  |  | 1 | New | 5 | Tuấn Thắng
T22 | Implement Unit Test , Integrated Test , System Test Customer Manage |  |  |  | 1 | New | 20 | Tuấn Thắng
Motor Type Manage
T23 | Draw Usecase Motor type Manage |  |  | PB03 |  |  | 10 | Phúc
T24 | Analyse and design code Motor type Manage | [5 empty] | 20 | Phúc
T25 | Code: Add new motor type |  | RQ08 |  | 1 | New | 10 | Phúc Phương
T26 | Code: Update new motor type |  |  |  | 1 | New | 10 | Phúc Phương
T27 | Code: Find motor type Function |  |  |  | 1 | New | 10 | Phúc Phương
T28 | Code: Disable motor type |  |  |  | 1 | New | 10 | Phúc Phương
T29 | Integrate All functions Motor type Manage |  |  |  | 1 | New | 5 | Phúc Phương
T30 | Implement Unit Test , Integrated Test , System Test Motor type Manage |  |  |  | 1 | New | 20 | Phúc Phương
Motor Manage
T31 | Draw Usecase Motor Manage | [5 empty] | 10 | Phúc
T32 | Analyse and design code Motor Mange | [5 empty] | 20 | Phúc
T33 | Code: Create motor |  | RQ08 | PB03 | 1 | New | 10 | Phúc
T34 | Code: Update motor |  |  |  | 1 | New | 10 | Phúc
T35 | Code: Find motor Function |  |  |  | 1 | New | 5 | Phúc
T36 | Code: Disable motor type |  |  |  | 1 | New | 5 | Phúc
T37 | Code: Create new color of motor |  |  |  | 1 | New | 10 | Phúc Phương
T38 | Code: import motor from excel format | [5 empty] | 10 | Phúc Phương
T39 | Integrate All functions Motor Manage |  |  |  | 1 | New | 15 | Phúc Phương
T40 | Implement Unit Test , Integrated Test , System Test Motor Manage |  |  |  | 1 | New | 20 | Phúc Phương
All Package Comple
T41 | Imtegrate all package | [5 empty] | 30 | All Member
T42 | Implement Integrate Test | [5 empty] | 15 | All Member
T43 | Implement System Test. | [5 empty] | 25
Before start sprint
T44 | Test plan | [5 empty] | 6 | Phương
T45 | Training Plan | [5 empty] | 1 | Huy
T46 | Traning | [5 empty] | 20 | Thắng Huy
T47 | Project Plan | [5 empty] | 30 | Huy
T48 | Master Plan | [5 empty] | 10 | Huy
T49 | Analyse Data base | [5 empty] | 6 | Hưng
T50 | Draw ERD | [5 empty] | 7 | Hưng
T51 | Code SQL | [5 empty] | 20 | Hưng
T52 | main GUI | [5 empty] | 2 | Thắng
T53 | Quality Attribute | [5 empty] | 10 | Phương
T54 | Scope and Vision | [5 empty] | 3 | Phương
T55 | Constraint | [5 empty] | 3 | Phương
T56 | Customer Process | [5 empty] | 6 | Phương
T57 | Product backlog | [5 empty] | 4 | Phương
T58 | Write Sprint backlog | [5 empty] | 10 | Phương Thắng
T59 | Manage Burn Down Chart | [5 empty] | 15 | Thắng

## Release Backlog
Backlog ID | Backlog | STORY / FEATURE / REQUEST |  |  | Story ID | Priority | Business Value | Sprint# | State | Note
|  | As a/an [User role] | I want to [Goal] | So that [reason]
PB01 | Quan ly tin nhan | User | Set the start time, end time, and content will be sent SMS messages | I can remind customers to car maintenance in each time | RQ04 | 1 | High | 1 | New
|  | User | Have the program which automatically send a message each day | I can announce to customer who have enough conditions in the RQ04 and is not sended messages about my vehicle maintenance program | RQ05 | 1 | High | 1 | New
|  | User | Send the message to all my customer | We can send a message again when it has been error | RQ06 | 1 | High | 1 | New
|  | User | Review the history of messages sent to customers. | I know my program which implement well and all my customer know it | RQ10 | 3 | Medium | 1 | New
PB02 | Quan ly thong tin khach hang | User | Print a list of customers coming to the birthday | We can send a birthday card or a birthday message | RQ07 | 3 | High | 1 | New
| Quan ly thong tin khach hang | User | View my customer's information which like SMS Template.xls | I can manage the information of customer who buy my motorbikes | RQ02 | 2 | Medium | 1 | New
| Quan ly thong tin khach hang | User | Import my customer's information from file excel (like SMS Template.xls) | I can create the list of customer's information quickly | RQ03 | 2 | High | 1 | New
PB03 | Quan ly xe | User | View my motorbike's information include : categories, colors, price, inventory | I can manage the information of motorbike in my superstore | RQ08 | 3 | High | 1 | New

## Product Backlog
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
RQ01 | User | Tôi muốn chương trình có đăng nhập | Có 1 From đăng nhập gồm có: username & password, quên mật khẩu, lưu đăng nhập | 1 | Medium |  | New
RQ02 | User | Tôi muốn chương trình có quản lý điểm cấp 3 | chương trình gồm điểm thành phần, điểm tổng kết, học lực, số buổi nghỉ, hạnh kiểm, danh hiệu. Điểm thành phần gồm có 3 hệ số. Điểm tổng kết, sau khi gv nhập xong điểm hế số 3 thì tự động tính điểm trung bình. Sau khi có ĐTB thì hệ thống tự động đánh giá học lực cho học sinh qua điểm, Sau GVCN nhập số buổi nghỉ và hạnh kiểm, thì hệ thống tự động cập nhật danh hiệu của HS | 1 | Low |  | New
RQ03 | User | Tôi muốn chương trình cấp quyền cho các user | Phân quyền cho phòng văn thư quản lí thông tin của gv và hs. Phân quyền cho gv thêm điểm cho hs. Phân quyền cho hs chỉ được xem điểm và thông tin cá nhân của mình không được chỉnh sửa bất kì cái gì | 1 | High |  | New
RQ04 | User | Tôi muốn có 1 chức năng gửi phản hồi của học sinh | Để học sinh Feedback chất lượng giảng dạy của giáo viên(GV đến đúng giờ hay không ?, Mức độ truyền đạt) | 4 | Low |  | New
RQ05 | User | Tôi muốn có một chương trình xem thời khóa biểu cho học sinh | Để học sinh cập nhật được thời khóa biểu của mình, nếu nhà trường đổi lịch thì sẽ thông báo về cho HS trước 1 ngày để chuẩn bị | 2 | Medium |  | New
| User | Tôi muốn có chức năng quản lý bằng cấp | Quản lý bằng tốt nghiệp: Nhập các thông tin về bằng tốt nghiệp như: Số hiệu bằng, ngày đăng kí, người ký bằng,v.v.. Và in số cấp bằng tốt nghiệp. Quản lý chứng chỉ tin học, chứng chỉ ielts. | 4 | Medium |  | New
RQ07 | User | Tôi muốn chức năng quản lý thông báo | Để cho giáo viên thống báo số buổi nghỉ của học sinh, thông báo các sự kiện sắp diễn ra cho học sinh. Phòng văn thư thông báo cho giáo viên về lịch trình dạy, các sự kiện mà trường sắp tổ chức | 3 | Medium |  | New
RQ08 | User | Tôi muốn có một chương trình tìm kiếm học sinh để tra cứu thông tin và điểm | Để cho giáo viên dễ dàng tìm kiếm được học sinh muốn tìm thông qua MHS hoặc họ tên | 2 | Low |  | New
RQ09 | User | Tôi muốn có một chức năng đăng ký học thêm | Để cho học sinh đăng ký theo nguyện vọng của học sinh học nhưng môn mà học sinh còn yếu, nhà trường dựa theo số nv đkí để xếp lớp | 3 | Medium |  | Removed
RQ10 | User | Tôi muốn có một chức năng quản lý sự kiện | Để cho các CB-CNV-GV-HS trong nhà trường có thể đăng ký các tiết mục biểu diễn văn nghệ của nhà trường tổ chức, hoạt động ngoại khóa hàng năm v.v… | 4 | Medium |  | New
RQ11 | User | [5 empty] | Removed

## TASK
ID | NAME TASK | CODING
C01.1 - RQ01 | Chức năng Login | GUI: - Dựa vào hình hình ảnh IMGCO1 - Label Tiêu đều: "Đăng nhập vào chương trình quản lý" - Font: 18px - Mầu: Xanh Cả mã mầu - Font Style: Arial - Background Color: Mã mầu - Label ID và Pass: có tiêu đề như nào - Mã mầu - Kích thước - Font gì - TextField: độ dài hoặc rộng nếu có và có set font và mầu sắc - kích thước. - Button đăng nhập có text như nào: "Đăng Nhập" - đầy đủ các thông tin về fon chữ mầu sắc kích thước. - nút này cũng bao gồm kích thước mầu sắc của nút - Lab quên mật khẩu Coding: - Nếu đăng nhập thành công đúng mật khẩu và pass thì sẽ login đến màn nào đó có MÃ C02.3 - RQ02 Thông báo lỗi: - Kiểm tra TextField ID phải ký tự lớn hơn 5 và không chưa ký tự đặc biết nếu không thì sẽ thông báo lỗi Msg01: "Mời bạn nhập ID lớn hơn 5 ký tự" Msg02: "Mời bạn không nhập ký tự vào ID" Và cứ như thế với ô Password
C01.2 - RQ01 | Chức năng Quên Mật Khẩu | Lan
C02.1-RQ02 | Chức năng Thêm điểm cho HS | Thọ
C02.2-RQ02 | Chức năng Sửa điểm cho HS | Thọ
C02.3-RQ02 | Chức năng Xóa điểm cho HS | Thọ
C02.3-RQ02 | Chức năng điểm danh | Thọ
C02.4-RQ02 | Chức năng xem điểm | Thọ
C03.1-RQ03 | chức năng phân quyền cho Phòng Đào tạo | Nhất
C03.2-RQ03 | chức năng phân quyền cho Giáo viên | Nhất
C03.3-RQ03 | chức năng phân quyền cho Học sinh | Nhất
C04.1-RQ04 | chức năng gửi phản hồi của Giáo viên | Thảo
C04.2-RQ04 | chức năng gửi phản hồi Học sinh | Thảo
C05.1-RQ05 | chức năng quản lý lịch dạy (GV) | Đỗ Hùng
C05.2-RQ05 | chức năng quản lý lịch học (HS) | Đỗ Hùng
C05.3-RQ05 | chức năng quản lý lịch dạy và học (ĐT) | Đỗ Hùng
C06.1-RQ06 | chức năng quản lý bằng tốt nghiệp | Thông
C06.2-RQ06 | chức năng quản lý chứng chỉ Tiếng Anh | Thông
C06.3-RQ06 | chức năng quản lý bằng nghề | Thông
C07.1-RQ07 | chức năng thông báo của PĐT | Tân, Huyền
C07.1-RQ07 | chức năng thông báo của GV | Tân, Huyền
C07.1-RQ07 | chức năng thông báo của HS | Tân, Huyền
C08.1-RQ08 | chức năng tìm kiếm điểm | Hiếu
C08.2-RQ08 | chức năng tìm kiếm thông tin | Hiếu
C09.1-RQ09 | chức năng đăng ký học thêm | Quốc Hùng
C010.1-RQ010 | chức năng quản lý sự kiện của HS | Hoàng Vân
C010.2-RQ010 | chức năng quản lý sự kiện của SV | Hoàng Vân

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.